## Slide 1
Weekly Scrum Status Report
Digital Twin Team · Sprint 3
12 – 16 Oct 2026 (W42)
Prepared by Scrum Master

## Slide 2
Executive Summary
ACKE.in | Weekly Scrum Status | Digital Twin Team | Sprint 3 | W42
2
AT RISK
Two items blocked on external dependencies
24 of 40 story points completed at mid-sprint
Onboarding API and audit logging merged
SSO integration blocked on vendor sandbox access
Test environment instability cost about one day
Burndown slightly behind ideal; recoverable
60%
Sprint progress
24/40
Points done
5
Items done
2
Items blocked

## Slide 3
Sprint Goal & Burndown
ACKE.in | Weekly Scrum Status | Digital Twin Team | Sprint 3 | W42
3
SPRINT GOAL
Ship the self-service onboarding flow to staging with audit logging enabled.
COMMITTED
40 points · 60% done
Chart: Story points remaining
| D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10
Ideal | 40 | 35.6 | 31.1 | 26.7 | 22.2 | 17.8 | 13.3 | 8.9 | 4.4 | 0
Actual | 40 | 38 | 35 | 33 | 28 | 24

## Slide 4
Completed
ACKE.in | Weekly Scrum Status | Digital Twin Team | Sprint 3 | W42
4
ID | Item | Owner | Points
ACK-101 | Onboarding REST API endpoints | Asha | 8
ACK-104 | Audit log persistence layer | Ravi | 5
ACK-107 | Input validation for tenant creation | Meera | 3
ACK-110 | CI pipeline caching | Karthik | 5
ACK-112 | Staging environment seed script | Asha | 3
Notes: ACK-101: Merged with 92% coverage; OpenAPI spec published.

## Slide 5
In Progress
ACKE.in | Weekly Scrum Status | Digital Twin Team | Sprint 3 | W42
5
ID | Item | Owner | Points | Progress
ACK-102 | Onboarding UI wizard | Divya | 8 | 60%
ACK-105 | Audit log search screen | Ravi | 5 | 30%
ACK-108 | Role-based access checks | Meera | 5 | 50%
ACK-113 | Load test baseline | Karthik | 3 | 20%

## Slide 6
Blockers & Risks
ACKE.in | Weekly Scrum Status | Digital Twin Team | Sprint 3 | W42
6
BLOCKERS
RISKS
ACK-103 – SSO integration
Owner: Asha
Ask: Vendor sandbox credentials needed by Mon
ACK-109 – Email notification templates
Owner: Divya
Ask: Approved copy from Marketing
SSO vendor delay may miss sprint goal
Severity: HIGH · Owner: Asha
Mitigation: Mock SSO provider behind a feature flag
Shared test environment instability
Severity: MEDIUM · Owner: Karthik
Mitigation: Dedicated namespace requested from DevOps
Holiday leave reduces capacity next week
Severity: LOW · Owner: Scrum Master
Mitigation: Re-plan scope on Monday
Notes: ACK-103: Ticket raised with vendor on Tuesday; no response yet.

## Slide 7
Velocity
ACKE.in | Weekly Scrum Status | Digital Twin Team | Sprint 3 | W42
7
Chart: Story points
| S7 | S8 | S9 | S10 | S11
Committed | 34 | 36 | 38 | 38 | 40
Completed | 30 | 33 | 35 | 38 | 36
34.4
Average velocity
92%
Commitment reliability

## Slide 8
Next Week Plan
ACKE.in | Weekly Scrum Status | Digital Twin Team | Sprint 3 | W42
8
# | Planned work | Owner
1 | Complete onboarding UI wizard | Divya
2 | Deliver audit log search screen | Ravi
3 | Finish role-based access checks | Meera
4 | Unblock SSO via mock provider | Asha
5 | Run load test and publish baseline | Karthik

## Slide 9
Thank you
Questions and blocker decisions welcome
scrum@acke.in